## Prioritization
Rank | Feature | Reach | Impact | Confidence | Effort | RICE_Score | MVP | Rationale
1 | Publish to TastyTube | 5 | 5 | 5 | 2 | 62.50 | Yes | Highest direct value: it turns completed edits into published videos on the first-party platform, which is the clearest path to user value and business impact.
2 | Specify dataset | 4 | 4 | 5 | 2 | 40.00 | Yes | A clean training set is a prerequisite for every downstream ML workflow, so it deserves early priority despite being invisible to end users.
3 | Select and instruct labeling team | 4 | 4 | 5 | 2 | 40.00 | Yes | Annotation setup is a foundational dependency for supervised model quality and has strong execution confidence with manageable effort.
4 | Generate video captions | 5 | 4 | 4 | 3 | 26.67 | Yes | Caption generation removes a major creator bottleneck and improves both accessibility and video quality for most users most of the time.
5 | Create app to edit the clips and text | 5 | 5 | 4 | 4 | 25.00 | Yes | The editing surface is essential because creators need to review, correct, and finalize AI outputs before publishing.
6 | Generate video title | video description | and recipe summary | 4 | 4 | 4 | 3 | 21.33 | Yes | Metadata generation cuts posting friction and improves discoverability while still allowing the creator to edit outputs.
7 | Prepare data: Split videos into clips | 4 | 4 | 4 | 4 | 16.00 | Yes | Clip-level segmentation data is required to train the most important automation in the MVP: turning raw cooking footage into recipe steps.
8 | Prepare data: Apply labels | 4 | 4 | 4 | 4 | 16.00 | Yes | High-quality semantic labels are required for meaningful AI assistance in captions, recipes, and later classification workflows.
9 | Build ML model to clip video into individual recipe steps | 4 | 5 | 3 | 4 | 15.00 | Yes | This is the core automation leap in the product. Confidence is moderate because of model difficulty, but it is too central to exclude from MVP.
10 | Conduct exploratory user research | 3 | 2 | 4 | 3 | 8.00 | No | Important risk-reduction work, but excluded from the formal MVP list to stay within the assignment cap. In practice it should still happen before launch.
11 | Conduct usability testing | 3 | 2 | 4 | 3 | 8.00 | No | Also critical for launch quality, but excluded from the formal MVP feature count to preserve a ruthless, cap-compliant scope.
12 | Build ML model to classify recipe steps | 3 | 3 | 3 | 4 | 6.75 | No | Helpful enhancement, but the MVP can still provide strong value with segmentation, captions, metadata generation, and manual editing controls.
13 | Publish to YouVideo | 2 | 2 | 3 | 2 | 6.00 | No | Cross-platform publishing has value, but it is not required to prove the core TastyTube creation loop in the first release.
14 | Publish to TikTak | 2 | 2 | 3 | 2 | 6.00 | No | Deferred to reduce launch complexity and keep the team focused on the first-party publishing workflow.
15 | Publish to Fastgram | 2 | 2 | 3 | 2 | 6.00 | No | Same rationale as other external publishing targets: useful, but not essential to the MVP value path.
16 | Create Recipe Library | 2 | 2 | 3 | 3 | 4.00 | No | A good onboarding aid, but secondary to getting the core creation workflow working reliably.
17 | Translate into other languages | 2 | 3 | 3 | 5 | 3.60 | No | Strategically attractive, but too costly and too dependent on high-quality source outputs for the first launch.
18 | Build Extensions API | 1 | 2 | 2 | 5 | 0.80 | No | Platform extensibility is a long-term investment rather than a first-release necessity.

## MVP Roadmap
Roadmap_Order | Feature | In_MVP | Estimated_Sprints | Start_Sprint | End_Sprint | Primary_Dependencies | Primary_Resources
1 | Specify dataset | Yes | 1 | 1 | 1 | None | Data Scientist; Data Analyst
2 | Select and instruct labeling team | Yes | 1 | 1 | 1 | Specify dataset | AI Product Manager; Annotation Manager
3 | Prepare data: Split videos into clips | Yes | 2 | 2 | 3 | Select and instruct labeling team | Annotation Team; QA Lead
4 | Prepare data: Apply labels | Yes | 2 | 3 | 4 | Prepare data: Split videos into clips | Annotation Team; QA Lead
5 | Build ML model to clip video into individual recipe steps | Yes | 2 | 5 | 6 | Prepare data: Apply labels | ML Engineer; Data Scientist
6 | Generate video captions | Yes | 1 | 6 | 7 | Build ML model to clip video into individual recipe steps | ML Engineer; Backend Engineer
7 | Generate video title | video description | and recipe summary | Yes | 1 | 7 | 7 | Generate video captions | ML Engineer; Prompt Engineer
8 | Create app to edit the clips and text | Yes | 2 | 5 | 8 | Build ML model to clip video into individual recipe steps | Mobile Engineer; UX Designer
9 | Publish to TastyTube | Yes | 1 | 9 | 9 | Create app to edit the clips and text; Generate video captions; Generate video title, video description, and recipe summary | Mobile Engineer; Backend Engineer

## Validation
ProductManager TastyTube Submission
Generated: 2026-06-18
Included tabs:
- Prioritization (RICE scoring, MVP selection, rationale)
- MVP Roadmap (sequencing, sprints, dependencies, resources)
Source files:
PRIORITIZATION_TAB.csv
MVP_ROADMAP_TAB.csv
Validation reference:
VALIDATION_REPORT.md